## Sheet1
Developer | Date and Time | Alloted By | Project | Job/Task | Estimation | Start Time | End Time | Time Worked | Status | Remarks
Ashish | 6/29/2023 | Vikrant Sir | Client Signup | Client Signup Manually Postman API |  | 9:30 | 11:30 | 2:00 | Done | I have completed the signup API. I have managed the referral ID dynamically. I share the API by email.
| 6/29/2023 | Mahesh Jannepalli | LSQ | UCC permit to trade flag updated in LSQ as Account Opened |  | 11:30 | 12:30 | 0:30 | Done | I reviewed the code first and completed the points as discussed, 12 pm crone job when you set then pass current date and 10am time and for 8 pm pass current date and 5pm time..
| 6/29/2023 | Ravina Dhaware ans Vivek SIr | Multiple Points | 1.VIJAY CHAUDHARY- Y0909910-4999 plan Activation |  | 14:00 | 18:30 | 5:00 | Done
2.Whatsapp message on partner link generation
3.Payment Issue Check
4.Ekyc Points check
| 6/29/2023 | Vivek Agrawal | Bill Desk | Bill Desk documents points |  |  |  |  | Pending | We got the Issue in the Enc API and We don't get any soution by the Java team and so we didn't do any work on it.
Ashwini | 2023-06-29 10:00 | Ashish Dubey | Billdesk | Proceed for the further API for trasaction verification to complete the billdesk process , | 1 hours | 10:00 | 12:00 |  | Pending | Having issues in java Encryption and decryption API to proceed further in billdesk
| 2023-06-29 12:00 | Vivek sir | EKYC | EKYC journey explained by tripti mam | 30 mins | 12:00 | 12:30 |  | Done
| 2023-06-29 12:30 | developers meeting |  |  |  | 12:30 | 13:00
| 29/06/23 2PM | Vivek sir | EKYC | Review code and flow for ekyc and find out the solutions for the live issues. : parner code not showing on thankyou page. |  | 14:00 | 6:30PM |  | Done
Shweta | 2023-06-29 | tripti maam | ekyc-web | pan-verify api and validations | 6 hours | 10:30 | 4:30 | 6 hours | done
Kumer | 2023-06-29 | Vivek sir | eKYC Web Design | worked on responsive design for tablets, small moniters, screen scale |  | 10:00 | 1:00 | 3
| 2023-06-29 | Vivek sir | Portfolio Evaluater | Worked on cart page, buy deatil page, sell detail page, |  | 1:30 | 6:30 | 5 | Working
Ajay | 29 June, 2023 | Giri | Portfolio evaluator | Worked on portfolio evaluator: Search screen, My Alert, Add Alert, Create GTT, Buy, Sell popup's and Currently working on Cart page and their popup. I have done all mobile screens | 8:30 | 10:20 | 6:30 | 8:30
Sumit | 29 Jun, 2023 |  | client & payment gateway Dashboard | 1.KT Client dashboard . | 4 hours | 12:00 | 16:00 | 4:00 hours | KT with gargie
2.KT payment gateway check view points.
3.API's login check credentials
Yogita | 6/29/2023 | Mahesh Jannepalli | Brokerage Dashboard | Create a csv file using api (Bank Mapping) | 6.00PM | 09:37:00AM | 05:15:00PM | DONE
Shital | 2023-06-29 | Mahesh Jannepalli | Dkyc App | Live support | 6.30PM | 10:00AM | 6.30 pm |  | Done
Sudipto | 29jun,2023 | Ravina | one click strategy | html coding of runlive know more page | 2 hours | 13:30 | 15:35 |  | Completed
Shrabhni | 29 June,2023 | Gargie | SSO | GL discussion, login redirection in live server | 10:30 | 12:00 |  | WIP | discussion done, waiting for implementation from GL side
|  | Ravina | One click strategy | One click strategy understanding | 12:00 | 12:30 |  | Done
|  |  | internal team meeting |  | 12:30 | 13:00 |  | Done
|  | Mahesh JI | SSL | SSL discussion | 13:00 | 13:30
|  | Ravina | One click strategy | SSO implementation & public strategy api integration | 15:00 |  |  | WIP